## 2019-Timeline
FACTOM 2019 PROCESS AND RATIFICATION TIMELINE - v.1.0 - 2019-02-18
Month | JANUARY |  |  |  |  | FEBRUARY |  |  |  | MARCH |  |  |  | APRIL |  |  |  | MAY |  |  |  | JUNE
Week number | WEEK 1 | WEEK 2 | WEEK 3 | WEEK 4 | WEEK 5 | WEEK 6 | WEEK 7 | WEEK 8 | WEEK 9 | WEEK 10 | WEEK 11 | WEEK 12 | WEEK 13 | WEEK 14 | WEEK 15 | WEEK 16 | WEEK 17 | WEEK 18 | WEEK 19 | WEEK 20 | WEEK 21 | WEEK 22 | WEEK 23 | WEEK 24 | WEEK 25 | WEEK 26
Date week starts | [10 empty] | 2019-03-11 | 2019-03-18 | 2019-03-25 | 2019-04-01 | 2019-04-08 | 2019-04-15 | 2019-04-22 | 2019-04-29 | 2019-05-06 | 2019-05-13 | 2019-05-20 | 2019-05-27 | 2019-06-03 | 2019-06-10 | 2019-06-17 | 2019-06-24
FIXED SCHEDULE
Grant Rounds |  |  |  |  | One full cycle takes 32 days | [5 empty] | 2019-04-15: One full grant cycle takes 45 days
ANO Election Rounds | bar: 2019-04-29 to 2019-05-27
Guide Elections
Amend Governance Document (Doc 001 - V1.4)
Amend Governance Document (Doc 001 - V1.5) | bar: 2019-04-22 to 2019-04-29
ANO Single use Election Round process ratification | bar: 2019-03-18 to 2019-04-01
Grant Round Process Document Ratification | bar: 2019-04-01 to 2019-04-08
Non-profit bylaws discussion | bar: 2019-03-11 to 2019-03-25
Non-profit bylaws Ratification/approval | bar: 2019-03-11 to 2019-03-18; 2019-06-03
Community Website Management Ratification | bar: 2019-03-18 to 2019-04-01
Working Group/Committee Restructure | bar: 2019-06-10 to 2019-06-24
Research expanding Standing Parties
Grant Success Process Ratification | bar: 2019-03-11
Grant sponsor Discussion | bar: 2019-03-11; 2019-06-17 to 2019-06-24
| July |  |  |  |  | August |  |  |  | September | 2019-04-08: October; 2019-05-06: November; 2019-06-03: December
ITEMS | WEEK 27 | WEEK 28 | WEEK 29 | WEEK 30 | WEEK 31 | WEEK 32 | WEEK 33 | WEEK 34 | WEEK 35 | WEEK 36 | WEEK 37 | WEEK 38 | WEEK 39 | WEEK 40 | WEEK 41 | WEEK 42 | WEEK 43 | WEEK 44 | WEEK 45 | WEEK 46 | WEEK 47 | WEEK 48 | WEEK 49 | WEEK 50 | WEEK 51 | WEEK 52
Date week starts | 2019-07-01 | 2019-07-08 | 2019-07-15 | 2019-07-22 | 2019-07-29 | 2019-08-05 | 2019-08-12 | 2019-08-19 | 2019-08-26 | 2019-09-02 | 2019-09-09 | 2019-09-16 | 2019-09-23 | 2019-09-30 | 2019-10-07 | 2019-10-14 | 2019-10-21 | 2019-10-28 | 2019-11-04 | 2019-11-11 | 2019-11-18 | 2019-11-25 | 2019-12-02 | 2019-12-09 | 2019-12-16 | 2019-12-23
FIXED SCHEDULE
Grant Rounds (tentative) | 2019-07-29: One full cycle takes 32 days; 2019-10-28: One full cycle takes 32 days
Amend Governance Document (Doc 001 - V1.6) | bar: 2019-10-28
ANO elections/removals document Ratification | bar: 2019-09-02 to 2019-09-09
Working Group/Committee Restructure Discussion | bar: 2019-08-26
Working Group/Committee Restructure Ratification | bar: 2019-10-28 to 2019-11-04
Testnet Governance | bar: 2019-10-14 to 2019-10-28
Doc 107 (grant process) amendment | bar: 2019-07-01 to 2019-07-08
https://www.epochconverter.com/weeks/2019

## 2020-Timeline
FACTOM 2020 PROCESS AND RATIFICATION TIMELINE - v.1.0 - 2019-12-05
Month | JANUARY |  |  |  |  | FEBRUARY |  |  |  | MARCH |  |  |  | APRIL |  |  |  |  | MAY |  |  |  | JUNE
Week number | WEEK 1 | WEEK 2 | WEEK 3 | WEEK 4 | WEEK 5 | WEEK 6 | WEEK 7 | WEEK 8 | WEEK 9 | WEEK 10 | WEEK 11 | WEEK 12 | WEEK 13 | WEEK 14 | WEEK 15 | WEEK 16 | WEEK 17 | WEEK 18 | WEEK 19 | WEEK 20 | WEEK 21 | WEEK 22 | WEEK 23 | WEEK 24 | WEEK 25 | WEEK 26 | WEEK 27
Date week starts | 2019-12-30 | 2020-01-06 | 2020-01-13 | 2020-01-20 | 2020-01-27 | 2020-02-03 | 2020-02-10 | 2020-02-17 | 2020-02-24 | 2020-03-02 | 2020-03-09 | 2020-03-16 | 2020-03-23 | 2020-03-30 | 2020-04-06 | 2020-04-13 | 2020-04-20 | 2020-04-27 | 2020-05-04 | 2020-05-11 | 2020-05-18 | 2020-05-25 | 2020-06-01 | 2020-06-08 | 2020-06-15 | 2020-06-22 | 2020-06-29
FIXED SCHEDULE
Grant Rounds | 2020-01-27: One full cycle takes 42 days; 2020-04-27: One full grant cycle takes 42 days
Guide Elections | bar: 2020-03-02 to 2020-03-16
AD-HOC EVENTS
Doc 007 | bar: 2019-12-30
ANO Server Number | bar: 2020-01-06 to 2020-01-13
Guide Election and Removal Process - V1.1 | bar: 2020-02-10 to 2020-02-24
Removal: DBGrow (Guide) | bar: 2020-02-17 to 2020-02-24
Document 107 - Factom Grant Process - v1.2 | bar: 2020-02-17 to 2020-03-02
Proposal to remove the Guide position | bar: 2020-02-17 to 2020-03-02
Doc 100 - No min threshold to being a Guide | bar: 2020-02-17 to 2020-03-02
| JULY |  |  |  | AUGUST |  |  |  |  | SEPTEMBER |  |  |  | OCTOBER |  |  |  |  | NOVEMBER |  |  |  |  | DECEMBER
ITEMS | WEEK 27 | WEEK 28 | WEEK 29 | WEEK 30 | WEEK 31 | WEEK 32 | WEEK 33 | WEEK 34 | WEEK 35 | WEEK 36 | WEEK 37 | WEEK 38 | WEEK 39 | WEEK 40 | WEEK 41 | WEEK 42 | WEEK 43 |  | WEEK 44 | WEEK 45 | WEEK 46 | WEEK 47 | WEEK 49 | WEEK 50 | WEEK 51 | WEEK 52 | WEEK 53
Date week starts | 2020-07-06 | 2020-07-13 | 2020-07-20 | 2020-07-27 | 2020-08-03 | 2020-08-10 | 2020-08-17 | 2020-08-24 | 2020-08-31 | 2020-09-07 | 2020-09-14 | 2020-09-21 | 2020-09-28 | 2020-10-05 | 2020-10-12 | 2020-10-19 | 2020-10-26 |  | 2020-11-02 | 2020-11-09 | 2020-11-16 | 2020-11-23 | 2020-11-30 | 2020-12-07 | 2020-12-14 | 2020-12-24 | 2020-12-28
FIXED SCHEDULE
Grant Rounds | 2020-07-27: One full cycle takes 42 days; 2020-10-26: One full grant cycle takes 42 days
AD-HOC EVENTS
https://www.epochconverter.com/weeks/2019