## TEMPLATE
!!!!!!!! THIS IS A TEMPLATE !!!!!! MAKE A COPY OF THIS SHEET BEFORE STARTING TESTING !!!!!!!
Test no. | Test | Task no. | Task | Executed By | Step no. | Step | Expected result | Pass/Fail | Comments
1 | Update 2 Authority Nodes |  |  | Testnet Admin or delegated
|  | 1.1 | Update follower node #1 to new factomd version
[5 empty] | 1.1a | Update follower node to new version | Pull and run new version with current flags and no errors
[5 empty] | 1.1b | Take note of how many minutes pass until node comes out of IGNORE STATE | 20 minutes (if not rebuilding savestate file) |  | Replace this text with number of minutes
[5 empty] | 1.1c | Monitor CPU/RAM-usage | Consistent with current version or better if improvements expected
[5 empty] | 1.1d | Verify that savestate file is built correctly if applicable | Savestate file built from scratch or updated as required
|  | 1.2 | Update follower node #2 to new factomd version
[5 empty] | 1.2a | Update follower node to new version | Pull and run new version with current flags and no errors
[5 empty] | 1.2b | Take note of how many minutes pass until node comes out of IGNORE STATE | 20 minutes (if not rebuilding savestate file)
[5 empty] | 1.2c | Monitor CPU/RAM-usage | Consistent with current version or better if improvements expected
[5 empty] | 1.2d | Verify that savestate file is built correctly if applicable | Savestate file built from scratch or updated as required
|  | 1.3 | Brain-Transfer Authority Identity #1 to follower node #1
[5 empty] | 1.3a | Set brain-transfer from Authority Node #1 to updated follower node #1 (5 blocks into future) | Succseful brain-transfer, updated follower #1 will host authority identity
[5 empty] | 1.3.b | Monitor CPU/RAM-usage after transfer | Verify that CPU/RAM-usage is as expected
[5 empty] | 1.3c | Verify that node is following minutes | Node following minutes as expected
|  | 1.4 | Brain-Transfer Authority Identity #2 to follower node #2
[5 empty] | 1.4a | Set brain-transfer from Authority Node #2 to updated follower node #2 (5 blocks into future) | Succseful brain-transfer, updated follower #2 will host authority identity
[5 empty] | 1.4.b | Monitor CPU/RAM-usage after transfer | Verify that CPU/RAM-usage is as expected
[5 empty] | 1.4c | Verify that node is following minutes | Node following minutes as expected
|  | 1.5 | Brain-Transfer Authority Identity #1 back to original node
[5 empty] | 1.5a | Update "Authority Node #1" to new factomd-version | Pull and run new version with current flags and no errors
[5 empty] | 1.5b | Take note of how many minutes pass until node comes out of IGNORE STATE | 20 minutes (if not rebuilding savestate file) |  | Replace this text with number of minutes
[5 empty] | 1.5c | Monitor CPU/RAM-usage | Consistent with current version or better if improvements expected
[5 empty] | 1.5d | Verify that savestate file is built correctly if applicable | Savestate file built from scratch or updated as required
[5 empty] | 1.5e | Set brain-transfer from follower node #1 to updated Authority Node #1 (5 blocks into future) | Succseful brain-transfer, updated Authority Node #1 will host authority identity
[5 empty] | 1.5f | Monitor CPU/RAM-usage after transfer | Verify that CPU/RAM-usage is as expected
[5 empty] | 1.5g | Verify that node is following minutes | Node following minutes as expected
|  | 1.6 | Brain-Transfer Authority Identity #2 back to original node
[5 empty] | 1.6a | Update "Authority Node #1" to new factomd-version | Pull and run new version with current flags and no errors
[5 empty] | 1.6b | Take note of how many minutes pass until node comes out of IGNORE STATE | 20 minutes (if not rebuilding savestate file) |  | Replace this text with number of minutes
[5 empty] | 1.6c | Monitor CPU/RAM-usage | Consistent with current version or better if improvements expected
[5 empty] | 1.6d | Verify that savestate file is built correctly if applicable | Savestate file built from scratch or updated as required
[5 empty] | 1.6e | Set brain-transfer from follower node #1 to updated Authority Node #1 (5 blocks into future) | Succseful brain-transfer, updated Authority Node #1 will host authority identity
[5 empty] | 1.6f | Monitor CPU/RAM-usage after transfer | Verify that CPU/RAM-usage is as expected
[5 empty] | 1.6g | Verify that node is following minutes | Node following minutes as expected
2 | Split-versioned Network |  |  | Testnet Admin
|  | 2.1 | Coordinate with Testnet-ANOs instructing them to update approximately 12 Authority Nodes.
[5 empty] | 2.1a | Coordinate with Testnet-ANOs instructing them to update approximately 12 Authority Nodes. | Updates and brain-transfers executed nominally in accordance with steps 1.1, 1.3 and 1.5 |  | Testnet-ANOs should be instructed to update in accordance with test procedures in 1.1, 1.3 and 1.5 and provide feedback regarding any issues.
[5 empty] | 2.2b | Verify that approximately half of Authority Nodes have been updated to new factomd version. Take action to correct if too many/too few have updated | Current testnet Authority Set cotnains approximately 24 nodes, so around 12 should be updated
|  | 2.2 | Apply load to network | Testnet Admin or delegated
[5 empty] | 2.2a | Apply 3 TPS for minimum 1 hour | Network should continue to operate nominally.
[5 empty] | 2.2b | Verify that holding queues are at an accepable level | < 100
|  | 2.3 | Execute authority elections | Testnet Admin or delegated
[5 empty] | 2.3a | Force 3 elections by killing federated nodes in seperate blocks | Should trigger elections, promoting audit servers to replace killed federated nodes
[5 empty] | 2.3b | Perform 2 elections within the same block by killing 2 federated nodes simultaneously | Should trigger two elections, promoting audit servers to replace killed federated nodes
|  | 2.4 | Execute network restart | Testnet Admin
|  |  |  | Steven | 2.4a | Verify that a load of 3 TPS is still ongoing.
|  |  |  | Steven | 2.4b | Take down network by stopping authority nodes via portainer system | Network should pause.
|  |  |  | Steven | 2.4c | Bring up network via portainer system | Network should restart without elections
|  | 2.5 | Verify that entries are not getting dropped at higher load | Testnet Admin or delegated
[5 empty] | 2.5a | Apply 5 TPS | Network should continue to operate nominally
[5 empty] | 2.5b | Verify that holding queues are not excessive on minimum 2 federated nodes (wait at least a hour) | < 100
[5 empty] | 2.5c | Run a script that keeps a list of entries acknowledged by the network, and verify that they are present in written blocks | No entries should be dropped
3 | Fully updated network |  |  | Testnet Admin
|  | 3.1 | Instruct the remaining Testnet-ANOs to update all Authority Nodes to new factomd version
[5 empty] | 3.1a | Make Discord-announcements requesting Testnet-ANOs to update Authority Nodes within 48 hours
[5 empty] | 3.1.b | Verify that at least 80% of the Authority Set has updated | At least 80% of the Authority Set should have updated
|  | 3.2 | Apply load to network | Testnet Admin or delegated
[5 empty] | 3.2a | Apply 3 TPS for minimum 1 hour | Network should continue to operate nominally.
[5 empty] | 3.2b | Verify that holding queues are at an accepable level | < 100
|  | 3.3 | Execute authority elections
[5 empty] | 3.3a | Force 3 elections by killing federated nodes in seperate blocks | Should trigger elections, promoting audit servers to replace killed federated nodes
[5 empty] | 3.3b | Perform 2 elections within the same block by killing 2 federated nodes simultaneously | Should trigger two elections, promoting audit servers to replace killed federated nodes
|  | 3.4 | Execute network restart
|  |  |  | Steven | 3.4a | Verify that a load of 3 TPS is still ongoing. | ~ 3 TPS
|  |  |  | Steven | 3.4b | Take down network by stopping authority nodes via portainer system | Network should pause.
|  |  |  | Steven | 3.4c | Bring up network via portainer system | S
|  | 3.5 | Verify that entries are not getting dropped at higher load | Testnet Admin or delegated
[5 empty] | 3.5a | Apply 5 TPS | Network should continue to operate nominally
[5 empty] | 3.5b | Verify that holding queues are not excessive on minimum 2 federated nodes (wait at least a hour) | < 100
[5 empty] | 3.5c | Run a script that keeps a list of entries acknowledged by the network, and verify that they are present in written blocks | No entries should be dropped
4 | Report on findings |  |  | Testnet Admin
|  | 4.1 | Report findings to community
[5 empty] | 4.1a | Create a post in the "Technical Discussion"-section on the protocol forum summarizing the findings from testing
[5 empty] | 4.1b | Make an announcement in #testnet-announcements tagging @testnet gnomes including a link to the above forum post

## Bond Release
Testing suite for factomd Bond Release
Test no. | Test | Task no. | Task | Executed By | Step no. | Step | Expected result | Pass/Fail | Comments
1 | Update 2 Authority Nodes |  |  | Testnet Admin or delegated
|  | 1.1 | Update follower node #1 to new factomd version
[5 empty] | 1.1a | Update follower node to new version | Pull and run new version with current flags and no errors
[5 empty] | 1.1b | Take note of how many minutes pass until node comes out of IGNORE STATE | 20 minutes (if not rebuilding savestate file) |  | Replace this text with number of minutes
[5 empty] | 1.1c | Monitor CPU/RAM-usage | Consistent with current version or better if improvements expected
[5 empty] | 1.1d | Verify that savestate file is built correctly if applicable | Savestate file built from scratch or updated as required
|  | 1.2 | Update follower node #2 to new factomd version
[5 empty] | 1.2a | Update follower node to new version | Pull and run new version with current flags and no errors
[5 empty] | 1.2b | Take note of how many minutes pass until node comes out of IGNORE STATE | 20 minutes (if not rebuilding savestate file)
[5 empty] | 1.2c | Monitor CPU/RAM-usage | Consistent with current version or better if improvements expected
[5 empty] | 1.2d | Verify that savestate file is built correctly if applicable | Savestate file built from scratch or updated as required
|  | 1.3 | Brain-Transfer Authority Identity #1 to follower node #1
[5 empty] | 1.3a | Set brain-transfer from Authority Node #1 to updated follower node #1 (5 blocks into future) | Succseful brain-transfer, updated follower #1 will host authority identity
[5 empty] | 1.3.b | Monitor CPU/RAM-usage after transfer | Verify that CPU/RAM-usage is as expected
[5 empty] | 1.3c | Verify that node is following minutes | Node following minutes as expected
|  | 1.4 | Brain-Transfer Authority Identity #2 to follower node #2
[5 empty] | 1.4a | Set brain-transfer from Authority Node #2 to updated follower node #2 (5 blocks into future) | Succseful brain-transfer, updated follower #2 will host authority identity
[5 empty] | 1.4.b | Monitor CPU/RAM-usage after transfer | Verify that CPU/RAM-usage is as expected
[5 empty] | 1.4c | Verify that node is following minutes | Node following minutes as expected
|  | 1.5 | Brain-Transfer Authority Identity #1 back to original node
[5 empty] | 1.5a | Update "Authority Node #1" to new factomd-version | Pull and run new version with current flags and no errors
[5 empty] | 1.5b | Take note of how many minutes pass until node comes out of IGNORE STATE | 20 minutes (if not rebuilding savestate file) |  | Replace this text with number of minutes
[5 empty] | 1.5c | Monitor CPU/RAM-usage | Consistent with current version or better if improvements expected
[5 empty] | 1.5d | Verify that savestate file is built correctly if applicable | Savestate file built from scratch or updated as required
[5 empty] | 1.5e | Set brain-transfer from follower node #1 to updated Authority Node #1 (5 blocks into future) | Succseful brain-transfer, updated Authority Node #1 will host authority identity
[5 empty] | 1.5f | Monitor CPU/RAM-usage after transfer | Verify that CPU/RAM-usage is as expected
[5 empty] | 1.5g | Verify that node is following minutes | Node following minutes as expected
|  | 1.6 | Brain-Transfer Authority Identity #2 back to original node
[5 empty] | 1.6a | Update "Authority Node #1" to new factomd-version | Pull and run new version with current flags and no errors
[5 empty] | 1.6b | Take note of how many minutes pass until node comes out of IGNORE STATE | 20 minutes (if not rebuilding savestate file) |  | Replace this text with number of minutes
[5 empty] | 1.6c | Monitor CPU/RAM-usage | Consistent with current version or better if improvements expected
[5 empty] | 1.6d | Verify that savestate file is built correctly if applicable | Savestate file built from scratch or updated as required
[5 empty] | 1.6e | Set brain-transfer from follower node #1 to updated Authority Node #1 (5 blocks into future) | Succseful brain-transfer, updated Authority Node #1 will host authority identity
[5 empty] | 1.6f | Monitor CPU/RAM-usage after transfer | Verify that CPU/RAM-usage is as expected
[5 empty] | 1.6g | Verify that node is following minutes | Node following minutes as expected
2 | Split-versioned Network |  |  | Testnet Admin
|  | 2.1 | Coordinate with Testnet-ANOs instructing them to update approximately 12 Authority Nodes.
[5 empty] | 2.1a | Coordinate with Testnet-ANOs instructing them to update approximately 12 Authority Nodes. | Updates and brain-transfers executed nominally in accordance with steps 1.1, 1.3 and 1.5 |  | Testnet-ANOs should be instructed to update in accordance with test procedures in 1.1, 1.3 and 1.5 and provide feedback regarding any issues.
[5 empty] | 2.2b | Verify that approximately half of Authority Nodes have been updated to new factomd version. Take action to correct if too many/too few have updated | Current testnet Authority Set cotnains approximately 24 nodes, so around 12 should be updated
|  | 2.2 | Apply load to network | Testnet Admin or delegated
[5 empty] | 2.2a | Apply 3 TPS for minimum 1 hour | Network should continue to operate nominally.
[5 empty] | 2.2b | Verify that holding queues are at an accepable level | < 100
|  | 2.3 | Execute authority elections
[5 empty] | 2.3a | Force 3 elections by killing federated nodes in seperate blocks | Should trigger elections, promoting audit servers to replace killed federated nodes
[5 empty] | 2.3b | Perform 2 elections within the same block by killing 2 federated nodes simultaneously | Should trigger two elections, promoting audit servers to replace killed federated nodes
|  | 2.4 | Execute network restart
|  |  |  | Steven | 2.4a | Verify that a load of 3 TPS is still ongoing.
|  |  |  | Steven | 2.4b | Take down network by stopping authority nodes via portainer system | Network should pause.
|  |  |  | Steven | 2.4c | Bring up network via portainer system | Network should restart without elections
|  | 2.5 | Verify that entries are not getting dropped at higher load | Testnet Admin or delegated
[5 empty] | 2.5a | Apply 5 TPS | Network should continue to operate nominally
[5 empty] | 2.5b | Verify that holding queues are not excessive on minimum 2 federated nodes (wait at least a hour) | < 100
[5 empty] | 2.5c | Run a script that keeps a list of entries acknowledged by the network, and verify that they are present in written blocks | No entries should be dropped
3 | Fully updated network |  |  | Testnet Admin
|  | 3.1 | Instruct the remaining Testnet-ANOs to update all Authority Nodes to new factomd version
[5 empty] | 3.1a | Make Discord-announcements requesting Testnet-ANOs to update Authority Nodes within 48 hours
|  |  |  | Rene | 3.1.b | Verify that at least 80% of the Authority Set has updated | At least 80% of the Authority Set should have updated | Pass
|  | 3.2 | Apply load to network | Testnet Admin or delegated
|  |  |  | Rene | 3.2a | Apply 3 TPS for minimum 1 hour | Network should continue to operate nominally. | Pass
|  |  |  | Rene | 3.2b | Verify that holding queues are at an accepable level | < 100 | Pass
|  | 3.3 | Execute authority elections
[5 empty] | 3.3a | Force 3 elections by killing federated nodes in seperate blocks | Should trigger elections, promoting audit servers to replace killed federated nodes
[5 empty] | 3.3b | Perform 2 elections within the same block by killing 2 federated nodes simultaneously | Should trigger two elections, promoting audit servers to replace killed federated nodes
|  | 3.4 | Execute network restart
|  |  |  | Steven | 3.4a | Verify that a load of 3 TPS is still ongoing.
|  |  |  | Steven | 3.4b | Take down network by stopping authority nodes via portainer system | Network should pause.
|  |  |  | Steven | 3.4c | Bring up network via portainer system | Network should restart without elections
|  | 3.5 | Verify that entries are not getting dropped at higher load | Testnet Admin or delegated
|  |  |  | Rene | 3.5a | Apply 5 TPS | Network should continue to operate nominally | Pass | During test 1 Luap applied up to 13TPS with the network being stable and usable
|  |  |  | Rene | 3.5b | Verify that holding queues are not excessive on minimum 2 federated nodes (wait at least a hour) | < 100 | Pass
|  |  |  | Luap | 3.5c | Run a script that keeps a list of entries acknowledged by the network, and verify that they are present in written blocks | No entries should be dropped | Pass
4 | Report on findings |  |  | Testnet Admin
|  | 4.1 | Report findings to community
[5 empty] | 4.1a | Create a post in the "Technical Discussion"-section on the protocol forum summarizing the findings from testing
[5 empty] | 4.1b | Make an announcement in #testnet-announcements tagging @testnet gnomes including a link to the above forum post