## Doc001-Amendment-2019-Q1
Factom Governance Document (Doc 001) - Suggested Amendments - 2019 - Q1 - V1.4
0. Definitions
What to amend | Doc Reference | Why amendment is required | Prerequisites | Required action before amendment | Time of amendment? | Status | Notes
Standing Party Definition | Page 7 | Wording to allow for future expansion | None | Ratification Discussion and vote | Version 1.4 | Changes drafted | See comments on Doc 001 for proposed changes.
1. Introduction
What to amend | Doc Reference | Why amendment is required | Prerequisites | Required action before amendment | Time of amendment? | Status | Notes
Logo | Header | Update to new community logo | New logo available | Ratification Discussion and vote | Version 1.4 | New logo available
Authority Servers --> Authority Set | 1.1 | More accurate wording | None | Ratification Discussion and vote | Version 1.4 | Changes drafted | See suggestion on Draft Doc 001 for proposed changes.
Version control matrix | Beginning of document | Standardize our governance documnets | None | Ratification Discussion and vote | Version 1.4 | Changes drafted | See suggestion on Draft Doc 001 for proposed changes.
2. Guides
What to amend | Doc Reference | Why amendment is required | Prerequisites | Required action before amendment | Time of amendment? | Status | Notes
Guide removal text | 2.1.4 | Superseded and expanded by Doc 100 | None | Ratification Discussion and vote | Version 1.4 | Changes drafted | See comments on Doc 001 for proposed changes.
Guide team makeup | 2.3 | Superseded and expanded by Doc 100 | None | Ratification Discussion and vote | Version 1.4 | Text suggested deleted | See comments on Doc 001 for proposed changes.
Description/ratification of Initial guides | 2.4.1 | Obsolute considering it has been a year since the initial guides were elected. | None | Ratification Discussion and vote | Version 1.4 | Text suggested deleted | See doc 100.
Voting description | 2.5 | In conflict with Doc 100/obsolete | None | Ratification Discussion and vote | Version 1.4 | Text Suggested deleted | See comments on Doc 001 for proposed changes.
New text: Description of guide process | 2.4 (if above suggestions are accepted) | Doc 001 needs to refer to ratified guide process | None at this stage (required Doc 100 which is ratified) | Ratification Discussion and vote | Version 1.4 | New text inserted as suggestion | See comments on Doc 001 for proposed changes.
3. Authority Set
What to amend | Doc Reference | Why amendment is required | Prerequisites | Required action before amendment | Time of amendment? | Status | Notes
Reference to guard nodes | 3.3.5.2 | Obselete | None | Ratification discussion and vote | Version 1.4 | Changes drafted | See comments on Doc 001 for proposed changes.
Guide's signing protocol messages | 3 | Guides do not and have not signed messages. | None | Ratification discussion and vote | Version 1.4 | Changes drafted | See comments on Doc 001 for proposed changes.
Authority set removal | 3.4.1 | Superseded and expanded by Doc 101 | None | Ratification discussion and vote | Version 1.4 | Changes drafted | See comments on Doc 001 for proposed changes.
Authority set removal | 3.4.2 | Document referenced "nodes" being removed; but it is the ANO itself that gets removed from the authority set. Specify that the ANO election process will be used to re-enter the Authority set. | None | Ratification discussion and vote | Version 1.4 | Changes drafted | See comments on Doc 001 for proposed changes.
Section about removal of standing party support | 3.4.3 | Text superseeded by ANO removal process for cause (Doc 101) | None at this stage (required Doc 101 which is ratified) | Ratification discussion and vote | Version 1.4 | Changes drafted | See comments on Doc 001 for proposed changes.
3.5 | 3.5 | Grammatical fix | None | Ratification discussion and vote | Version 1.4 | Changes drafted | See comments on Doc 001 for proposed changes.
3.6.1 | 3.6.1 | Sentence restructuring | None | Ratification discussion and vote | Version 1.4 | Changes drafted | See comments on Doc 001 for proposed changes.
5. Token Supply
What to amend | Doc Reference | Why amendment is required | Prequistes | Required action before amendment | Time of amendment? | Status | Notes
Remove irrelevant wording about M3. | 5.1.1 | Wording outdated and irrelevant. | None | Ratification discussion and vote | Version 1.4 | Changes drafted
7. Amendments
What to amend | Doc Reference | Why amendment is required | Prequistes | Required action before amendment | Time of amendment? | Status | Notes
Document amendment procedure | Chapter 7, Section 1 | Process in Doc 002 supercedes process as described in this chapter | None at this stage (required Doc 002 which is ratified) | Ratification discussion and vote | Version 1.4 | Changes drafted | See suggest amendment as well as comment.
New section | Chapter 7, Section 2 | Including reference to Doc 002 for creating additional governance and record documents | None at this stage (required Doc 002 which is ratified) | Ratification discussion and vote | Version 1.4 | Changes drafted | See suggest amendment as well as comment.