## Governance doc changes
Green = Document is okay
Blue = Document needs minor/simple work
Red = Needs more work/decissions
|  | Governance documents |  |  | David Chapmans review
Document | Paragraph | Reason | Suggested action | Priority | All Governance documents will need to be amended due to the “Document Control Matrix”. Suggested prioritization in column H. All other documents in a reasonable but non-rushed timeframe.
001 - Factom Governance | Doc control matrix | Mentions guide approval for doc changes | Remove | 2 | Doc 001 - Factom Governance
| chapter 2 | Introduces guides | Remove chapter altogether
| 4.1.4 | Mentions guide as potential sponsor | Remove guide
| 4.5 | Guide remuneration grant | Remove paragraph
| 6.2.3 | Guide support category | Remove paragraph
002 - Administration of governance and community documents | Doc control matrix | Mentions guide approval for doc changes | Remove | 1 | Doc 002 - Administration of Governance Documents
| 1.4 | Mentions guides as standing party | Remove "guide"
| 1.6 | Guides facilitating voting process | Reword in more generic terms
| 2.2 | Guide vote as phase 2 | Change to 2 phases, remove guide
| 2.3.1 | Suggests guides to store the document | Make the document creator/amendment responsible
| 2.3.6 | Mentions only the document creator is allowed to edit | This is technically incorrect and should be loosened
| 2.4 | Mentions guide doing a first vote | Remove clause altogether
| 2.5 | Mentions the outcome of the guide vote (quorum) | Reword to let the ANO vote be the first vote
| 2.6 | Suggests the guides incorporate the ratified document in the structure | Change to parties having worked on creation/ammending
| 2.7 |  | Update these documents
| 3.1 | Explains the control matrix. Several mentions of guides and their approvals | Reword to remove any guide references
| 3.2.1 | Example includes guides | Change example, to remove guides
| 3.2.3 | Version numbering scheme is now based on who voted | Change version numbering more inline with SEMVER for software
| 4.1.2 | Mentions ammedments and guides approval | Remove 4.1.2
| 4.1.3 | Mentions guide in the process | Remove guides
| 5.1 | Mentions guides performing the google drive work | Remove guides, make creator/ammenders responsible | 3 | Doc 107 - Factom Grant Process
003 - Authority Node Operator Expectations | - | No changes needed, does lack a control matrix
004 - Community Website Governance | Doc control matrix | Mentions guide approval for doc changes | Remove
| 2 & 2.1 | Explicitly mentions the website committee, rendering the doc invalid currently |  | 8 | All other documents in a reasonable but non-rushed timeframe.
| 2.2 | Mentions marketing & documentation committee (disolved)
| 3.1 | Mentions the guides involved in termination vote | Remove guides
005 - Factom Protocol ANO Promotion and Demotion System | Doc control matrix | Mentions guide approval for doc changes | Remove
| 2.8 | Mentions a vote to potentially increase ANO spots by the guides in a guide meeting | Problematic, as this means ANOs voting on this | 4 | Doc 005 - ANO Standing System
| 2.11 | Mentions guides | Remove guides
| 2.12 | Mentions guide organizing a binary support poll in case of dashboard failure | Organize differently. Make it mandatory for ANOs
| 3.3 | Mentions guides being the only ones to change the application questions | Organize differently. Probably normal document review process is fine
| 4.3 | Mentions guides announcing promotions/demotions | Organize differently
| 4.10 | Mentions guides updating doc 207 and 208 | Organize differently
006 - Working Group & Committee Framework | Doc control matrix | Mentions guide approval for doc changes | Remove | 5 | Doc 006 - Working Group & Committee Framework
| 1.1.6 | Guides updating Doc 209 | Make the respective chairman responsible for the update and follow doc ratification process
| 2.1.4 | Mentions guide vote | Remove guide vote mention
| 2.2.1 | Guides approval | Remove guides
| 2.2.5 | Guides eligable for vote | Remove guide vote mention
| 2.2.7 | Mentions guide | Remove guide vote mention
| 2.3.2 | Mentions guides | Remove mention
| 2.3.4 | Mentiond guides vote | Remove guide vote mention
| 2.4.2 | Mention of guide | Remove guide mention
| 2.4.3 | Mentions guides vote | Remove guides and guide vote
| 2.4.4 | Mentions guides | Remove guides
| 2.5.1 | Mentions guides | Remove guides
| 2.5.2 | Mentions guides | Remove guides
007 - Factom Testnet Governance | Doc control matrix | Mentions guide approval for doc changes | Remove | 6 | Doc 007 - Testnet Governance
| 7.2 | Mentions guides | Remove guides
| Apendix 6 | Mentions guides | Remove guides
| Apendix 8 | Guides are responsible for Testnet Admin elections | Make Standing parties responsible for elections, by appointing 1 point person per case
| A8 1.1.2 | Guides are responsible for Testnet Admin elections | Make Standing parties responsible for elections, by appointing 1 point person per case
| A8 1.1.5 | Guides make announcement | Change into appointed person
| A8 1.1.5.4.4. | Mentions guide vote | Remove guide vote
| A8 1.1.5.5.1 | Mentions guide vote | Remove guide vote
| A8 1.1.5.5.3 | Mentions guide vote | Remove guide vote
| A8 1.1.6 | Guides make announcement | Change into appointed person
| A8 1.2.1 | Mentions guides | Remove guides
| A8 1.2.4 | Mentions guides | Remove guides
| A8 1.2.4.1 | Mentions guides | Remove guides
| A8 1.2.4.2 | Mentions guides | Remove guides
| AB 1.2.4.4 | Mentions guides | Remove guides
| A8 1.2.4.8 | Mentions guides vote | Remove guides vote
| A8 1.2.5.2 | Guides make announcement | Change into appointed person
| A8 1.2.5.3 | Guides initiate election | Change into appointed person

## Process doc changes
Green = Document is okay
Blue = Document needs minor work
Red = Needs more work/decissions
Process documents
Document | Paragraph | Reason | Suggested action
100 - Guide Election and Removal Process | All | Well, kinda self explanatory :P | Remove doc |  | Governance Document to be Removed
101 - Removal of ANO from the Authority Set for Cause | Chapter 2 | Expects guides to be the gatekeeper and SPAM filter | Remove SPAM filter and immediately include all standing parties. This could have unintended side effects in standing if the removal does not go through for vote. This chapter would need a complete rewrite | 7 | Doc 101 - Removal of ANO from the Authority Set for Cause - It is suggested that the ANO Standing System be amended where if an ANO hits a certain extremely low threshold of Standing (10%?), they are automatically demoted to Candidate without the 90 days.
| 4.1.1 | Guides announce | Move to chappie
| Chapter 5 | Emergency suspension by guides | Needs to be rewritten
102 - 105 Placeholder (empty files)
106 - Factom Grant Success Determination Process | Doc control matrix | Mentions guides | Remove guides
| 2.6 | Mentions guides updating Doc 213 | Suggest to remove the spreadsheet altogether. It is something already in Factomize and like the standing dashboard could be extended there
107 - Factom Grant Process | Doc control matrix | Mentions guides | Remove guides
| 3.1 | Guides announce grant rounds | Make workinggroup or person responsible. Replace by automated system in Factomize/Discord longer term
| 3.3 | Guides are solely making announcements | Make workinggroup or person responsible. Replace by automated system in Factomize/Discord longer term
| 3.4 | Mentions guides | Remove guides
| 4.2 | Mentions guides in the timeline table | See above solutions
| 4.3.1 | Guides determine/calculate amount of FCT available in grantpool | Create small app that does it, making the above entity or automation responsible to list the amount
| 4.3.2 | Guides announce FCT available for grantround | Make workinggroup or person responsible. Replace by automated system in Factomize/Discord longer term
| 4.5.2 | Guides determine validity of grant | Make standing parties responsible
| 4.6 | Guides can do a fallback to manual grant rounds in case of grantround forum failure | Make standing parties responsible
| 4.6.2 | Guides can ammend grant round questions | Change guides to standing parties (document ratification vote)
| 4.8.1.1 | Guides can vote on grants | Remove guides
| 4.8.2.2. | Mentions guide pay | Remove guide pay
| 4.11 | Indemnication and waiver mentions guides several times | Update waiver

## Informational & records
Green = Document is okay
Blue = Document needs minor/simple work
Red = Needs more work/decissions
Informational & Records
Document | Paragraph | Reason | Suggested action
200 - Factom Community Documents | 1.2 | Mentions guide maintenance | Remove guides
| Table 1 | Guide related documents in several lines | Remove guide related documents from table
202 - Authority Server Minimum Specifications
203 - Cancellation of coinbase outputs
204 - Including a new ANO into the Authority Set | 8 | Mentions guides announcing | Make standing parties responsible, self organize. Move to automation later
| 9 | Mentions guide allert bot and form/spreadsheet | Make core committee responsible as it already handles emergencies from the technical perspective
205 - (PLACEHOLDER) Handling of sensitive information (GDPR)
206 - (PLACEHOLDER) Factom node update documentation
207 - Factom Authority Set Operators & Composition |  |  | Can be removed altogether, as the ANO dashboard replaced it
208 - Factom Authority Set Identities & node update tracking
209 - Factom Working Groups & Committees Register
210 - Factom Protocol Guide List |  |  | Retain as archived doc
212 - Factom M3 Authority Server Location Form (Responses)
213 - Awarded Factom Protocol Grants |  |  | Keeps track of all grants. Probably best to have Factomize give a matrix like overview like for ANOs. Can be done by standing parties in the mean time if desired
214 - Factom Grant Round Timelines (DOC 107, V.1.1)
215 - Grant Address Confirmations
216 - Process Discussion and Ratification Timeline |  | Mentions guides in the future in timelines | Remove future timelines pertaining guides
217 - Factom Protocol Grant Application Questions & Indemnification Clause | Ratification | Mentions guides for ratification | Include normal contol matrix without guides and remove mention of ratification process.
| Indemnification | Mentions guides in the indemnificaton | Remove guides
218 - Instructions: Updating nodes in Factom Authority Set
250 - TEMPLATE - General Document
251 - TEMPLATE - Meeting Minutes
252 - Factom Committee Application Template | 2.2 | Mentions guides can take part | Remove guides
| 2.5 | Mentions to ask a guide to upload document in governance drive | Change to Factomize document. Allow standing parties to upload
| Apendix A | Mentions guides | Change into standing parties

## Software to be updated
Software to be Updated
Ref | Action | Comments
1 | Automated Grant System
2 | Remove Guide role from voting
3 | Automate community platform announcements per Doc 107 with bots
4 | Provide final PR to Core Committee rather than Guides
5 | Create accounting system that automatically determines estimated and final amount of FCT available | In works. See https://github.com/TRGG3R/factom-grant-calc.git
6 | ANO Standing System
7 | Removal of Guide role
8 | Per Doc 005, Section 2.8, instead of the Guides voting twice per year in week 5 and 31 to add additional ANO slots, the other Standing Parties will be prompted by Chappie creating the vote automatically. | Niels Klomp: This is one of the most problematic things IMO. Why would some of the ANOs want more/less ANO spots?
9 | Doc 207 and Doc 208 shall be updated automatically or by the Core chair with ANO identities
10 | Document Ratification System
11 | Remove Guide ⅘ vote, update Chappie, Remove Guide vote
12 | Timed Discussions
13 | Remove Guide role
14 | Normal forum polls
15 | Remove Guide role

## Governance Process Automation
Governance Processes to Improve Through Automation
Ref | Description
1 | A Discord and Reddit bot will be created to help facilitate automated governance communication.
2 | Creation and amending of governance documents. The system would provide an easy process where anyone could create or amend governance documents. It would allow for line by line amending and voting rather than the all or nothing approach we currently have. Includes automatically uploading and Factomizing new/amended governance docs.
3 | Automated Testnet Elections per Doc 007.

## Other changes
Ref | Changes to Discord
1 | Removal of Guide role
2 | Remove Guide specific channels
Governance Forum Changes
1 | Remove https://factomize.com/forums/major-contributors/guides
2 | Amend https://factomize.com/forums/governance-info/
3 | Remove Guide usergroup
4 | Remove Guide Only forum
Other Changes
1 | Removal of the Governance Google Drive as it’s redundant. Provide regular backups of the governance forum to members of the Core and Website Committee.
Governance Documents to be Removed
1 | Factom Timeline - https://factomize.com/forums/documents/factom-governance-timeline.61/ -- automate use of the Calendar instead.